## Sheet1
Phase | Week | Day | Task | Category | Priority | Status | Est. Time (hrs) | Notes | Document Location
GATHER | 1 | 1-2 | Create master documentation checklist | Planning | High | Not Started | 1 | Use comprehensive checklist provided
GATHER | 1 | 1-2 | Search home files for receipts warranties permits | Documentation | High | Not Started | 2 | Check filing cabinets closet boxes
GATHER | 1 | 1-2 | Create digital folder structure on computer | Organization | High | Not Started | 0.5 | Mirror physical binder structure
GATHER | 1 | 1-2 | Download 24 months utility bills from providers | Financial | Medium | Not Started | 1 | Electric gas water sewer trash
GATHER | 1 | 1-2 | Request property tax bills last 3 years | Financial | Medium | Not Started | 0.5 | From county tax office
GATHER | 1 | 3-4 | Contact municipality for building permits | Documentation | High | Not Started | 1 | Call or visit planning department
GATHER | 1 | 3-4 | Reach out to contractors for invoice copies | Documentation | High | Not Started | 1.5 | Kitchen bath HVAC roof electrician plumber
GATHER | 1 | 3-4 | Gather all appliance manuals and warranties | Appliances | Medium | Not Started | 1 | Check kitchen drawer basement storage
GATHER | 1 | 3-4 | Locate original purchase documents | Property Info | High | Not Started | 1 | Closing papers inspection from purchase
GATHER | 1 | 5-6 | Take comprehensive photos of entire home | Photos | High | Not Started | 2 | All rooms from multiple angles
GATHER | 1 | 5-6 | Photograph all major systems | Photos | High | Not Started | 1 | HVAC water heater electrical panel sump
GATHER | 1 | 5-6 | Document serial numbers with photos | Photos | High | Not Started | 1 | All appliances HVAC systems
GATHER | 1 | 5-6 | Take exterior photos from all angles | Photos | Medium | Not Started | 0.5 | Front back both sides roof condition
GATHER | 1 | 7 | Schedule pre-listing home inspection | Inspections | Medium | Not Started | 0.5 | $300-$500 optional but valuable
GATHER | 1 | 7 | Schedule roof inspection if over 10 years | Inspections | High | Not Started | 0.5 | $150-$300 document condition
GATHER | 1 | 7 | Get HVAC service tune-up | Inspections | High | Not Started | 0.5 | $150-$300 creates recent record
GATHER | 1 | 7 | Order well water test if applicable | Inspections | High | Not Started | 0.5 | $50-$150 often required for sale
ORGANIZE | 2 | 8-9 | Organize all documents by category | Organization | High | Not Started | 2 | Use 9 categories from checklist
ORGANIZE | 2 | 8-9 | Scan all paper documents to PDF | Organization | High | Not Started | 2 | High resolution clear readable
ORGANIZE | 2 | 8-9 | Fill out home inventory template | Organization | Medium | Not Started | 2 | Excel template with all items
ORGANIZE | 2 | 8-9 | Create timeline of improvements | Organization | Medium | Not Started | 1 | Chronological list with costs
ORGANIZE | 2 | 10-11 | Write descriptions for renovations | Organization | High | Not Started | 2 | Kitchen bath basement details
ORGANIZE | 2 | 10-11 | Create before/after photo compilations | Photos | High | Not Started | 1.5 | Side by side comparisons impressive
ORGANIZE | 2 | 10-11 | Document system ages with proof | Documentation | High | Not Started | 1 | HVAC roof water heater electrical
ORGANIZE | 2 | 10-11 | Organize warranties by category | Documentation | Medium | Not Started | 1 | Appliances systems improvements
ORGANIZE | 2 | 12-13 | Purchase 3-ring binder dividers sheet protectors | Supplies | High | Not Started | 0.5 | $30-$50 at office supply store
ORGANIZE | 2 | 12-13 | Print key documents in color | Organization | High | Not Started | 1.5 | Before/afters permits receipts
ORGANIZE | 2 | 12-13 | Assemble physical binder with tabs | Organization | High | Not Started | 2 | Professional appearance matters
ORGANIZE | 2 | 12-13 | Create USB drive backup digital files | Organization | High | Not Started | 1 | $15-$30 buy multiple copies
ORGANIZE | 2 | 14 | Create neighborhood welcome guide | Community | Medium | Not Started | 2 | Schools parks restaurants services
ORGANIZE | 2 | 14 | Write utility cost summary one-page | Financial | High | Not Started | 1 | Average costs by season
ORGANIZE | 2 | 14 | Create property information summary | Property Info | High | Not Started | 1 | One-page home overview stats
ORGANIZE | 2 | 14 | Make list of preferred contractors | Services | Medium | Not Started | 1 | Plumber electrician HVAC landscaper
FINALIZE | 3 | 15-16 | Review all documentation for accuracy | Quality Check | High | Not Started | 2 | Verify dates costs details
FINALIZE | 3 | 15-16 | Update with recent changes | Updates | High | Not Started | 1 | New repairs bills maintenance
FINALIZE | 3 | 15-16 | Chase missing documentation | Documentation | High | Not Started | 1 | Follow up with contractors municipality
FINALIZE | 3 | 15-16 | Take final updated photos if needed | Photos | Medium | Not Started | 1 | Any changes since initial photos
FINALIZE | 3 | 15-16 | Create executive summary one-page | Summary | High | Not Started | 1.5 | Professional overview for buyers
FINALIZE | 3 | 17-18 | Review package with real estate agent | Agent Review | High | Not Started | 1 | Incorporate agent feedback
FINALIZE | 3 | 17-18 | Update listing description | Marketing | High | Not Started | 1 | Highlight documentation throughout
FINALIZE | 3 | 17-18 | Plan photo strategy for binder | Marketing | High | Not Started | 0.5 | Include in listing photos
FINALIZE | 3 | 17-18 | Create QR code for digital platform | Marketing | Medium | Not Started | 0.5 | If using MyHomePlatform
FINALIZE | 3 | 19-20 | Make multiple USB drive copies | Organization | Medium | Not Started | 0.5 | One per serious showing
FINALIZE | 3 | 19-20 | Practice documentation talking points | Preparation | High | Not Started | 1 | With agent rehearse highlights
FINALIZE | 3 | 19-20 | Plan binder placement for showings | Preparation | High | Not Started | 0.5 | Kitchen counter dining table
FINALIZE | 3 | 19-20 | Create display signage | Preparation | Medium | Not Started | 0.5 | Home Documentation—Please Review!
FINALIZE | 3 | 21 | Final walkthrough verify complete | Quality Check | High | Not Started | 1 | Check all 9 categories covered
FINALIZE | 3 | 21 | Update all information final time | Updates | High | Not Started | 1 | Most recent utility bills tax info
FINALIZE | 3 | 21 | Brief agent on highlights talking points | Agent Brief | High | Not Started | 1 | Key selling points statistics
FINALIZE | 3 | 21 | READY TO LIST! | Launch | High | Not Started | 0 | All documentation complete organized ready!